# Client Onboarding, 7-Day Launch Pipeline

Category: Onboarding Source: Module 3 Lesson 1, Module 3 Lesson 7 When to use: Client just signed and paid. Run this every time, no exceptions. Estimated time: 4 to 5 hours of your time across 7 days

## Prerequisites

- Contract signed (DocuSign or PandaDoc)

- First payment cleared

- Welcome email sent with onboarding form

## Checklist

- Day 1, Onboarding Call (30 min)

  - Walk through onboarding form together

  - Collect Meta Business Manager access (Partner level)

  - Collect website access for pixel install

  - Collect Google Analytics access (Viewer)

  - Request brand assets via shared Google Drive folder

  - Confirm primary offer and CTA

  - Set expectations: ads live within 7 days, real data after 5 to 7 days, weekly Monday updates, monthly call on the 1st

- Day 2, Research and Setup (60 min)

  - Set up or audit Meta ad account

  - Install Meta Pixel via GTM

  - Verify pixel firing with Meta Pixel Helper and Test Events

  - Add payment method to ad account

  - Run Nexus competitor and audience research

- Day 3 to 4, Creative Production (60 min)

  - Generate 12+ ad copy variations across PAS, AIDA, BAB, Story frameworks

  - Generate 15 to 25 creatives across 4+ formats (image, carousel, video, UGC, before/after)

  - Send top 3 to 5 creatives to client for written approval

- Day 5 to 6, Campaign Build + QA (45 min)

  - Build campaign per structure SOP, broad targeting, location radius set

  - Upload all creatives, Advantage Creative toggles OFF

  - Run pre-launch QA checklist

  - Do not publish yet

- Day 7, Launch + Monitor (25 min)

  - Publish campaigns, wait for Meta review (1 to 24 hours)

  - Text client: ads are live, 48-hour learning phase, real data after 3 to 5 days

  - Set up AI Campaign Optimizer with auto-pause rules

  - Schedule daily 15-min check-ins

  - Schedule first weekly report for next Monday

## Notes

- No work begins until payment clears.

- Record the onboarding call with permission.

- Naming convention for everything: [Client][Objective][Audience]_[Date].

- Same six-phase pipeline every time. Consistency is what lets one person run 10 clients.

## Related SOPs

- client-meta-access-request

- meta-pixel-install-gtm

- audience-research-nexus

- ad-copy-12-angle-generation

- ad-image-generation

- vortex-creative-diversity-check

- campaign-structure-naming

- targeting-setup-broad

- pre-launch-qa-checklist

- daily-15min-optimization-routine

- weekly-client-report